SLCM Mobile App (Flutter)

Effort estimation for the Student, Faculty and Parent portals

Version 1.0  |  15 October 2026  |  Companion workbook: SLCM_Mobile_App_Effort_Estimation.xlsx

1. Summary

2. Scope

3. Current state of the backend

Features with no backend today

4. Approach

App structure

Helpdesk

How the estimate was built

5. Common Foundation

6. Student Portal

7. Faculty Portal

8. Parent Portal

9. Team and timeline

Phased delivery

Ways to shorten or de-risk the timeline

10. Assumptions, exclusions and risks

Assumptions

Exclusions

Risks

11. Decisions needed before kick-off

# 1. Summary

The work is delivered by a team of 2 junior developers who handle the Flutter screens, backend APIs and testing between them. For an experienced developer the full scope would be 317.3 person-days of effort, including UAT, coordination and a 15% contingency. A person-day is one person working for one day; it is a measure of work, not of headcount.

Junior developers typically take about 1.5x as long, and each needs around 10 days to learn Flutter and the Frappe APIs first. That brings the effort to 495.9 person-days. Shared between 2 developers, delivery takes about 12 months (11.8 months of working time). Released in phases, the Student app can go live after about 8 months.

The APIs are not fully done. Most actions that write data (submit, pay, save) already have whitelisted APIs, but most screens that only display data (dashboards, results, attendance summaries, exam schedule, hostel details) are built inside server-rendered pages and have no JSON API. These need new endpoints, which is why every module has backend effort. The parent portal has the largest gap: 5 of its 12 features have no backend in the web portal today.

| Module | Features | Experienced developer (days) | Junior team effort (days) | Calendar months (team of 2) |
| --- | --- | --- | --- | --- |
| Common Foundation | 13 | 81.7 | 122.5 | 2.9 |
| Student Portal | 23 | 118.1 | 177.2 | 4.2 |
| Faculty Portal | 11 | 62.8 | 94.2 | 2.2 |
| Parent Portal | 12 | 54.7 | 82.0 | 2.0 |
| Ramp-up and learning (both developers) |  |  | 20.0 | 0.5 |
| Total | 59 | 317.3 | 495.9 | 11.8 |

Both day columns include UAT and bug-fixing (10%), coordination (10%) and contingency (15%). Junior team effort = experienced-developer effort x 1.5. Calendar months = junior team effort / (2 developers x 21 working days). All figures can be edited in the Summary sheet of the workbook.

# 2. Scope

Convert the three existing web portals in the SLCM Frappe app into one native mobile app for Android and iOS, built in Flutter:

- Student: 23 features from slcm/www/student-portal

- Faculty: 11 features from slcm/www/faculty-portal

- Parent / Guardian: 12 features from slcm/www/parent-portal

- Helpdesk: the helpdesk, embedded today as an iframe in each portal, is carried into the app.

The feature lists include everything requested, plus the helpdesk, notifications and profile screens that any mobile app needs. Web pages outside the request (Placement, Transcript Request, Fee Certificate, Enrollment) are excluded.

# 3. Current state of the backend

Each feature was checked against the portal code and the whitelisted methods in slcm/api. Features fall into three groups:

- Ready: a JSON API already exists. Mobile work is mostly Flutter UI.

- Partial: the action API exists (for example submit_leave_request), but the list or read data is computed in the page's get_context and returned as HTML. A JSON endpoint has to be added, reusing the same logic.

- Missing: no backend exists in the web portal today. Data model, permissions and APIs must be built.

| Module | Ready | Partial | Missing |
| --- | --- | --- | --- |
| Student Portal | 7 | 16 | 0 |
| Faculty Portal | 6 | 4 | 1 |
| Parent Portal | 2 | 5 | 5 |

All 40 portal pages render through get_context, so moving read logic into shared service functions that both the web page and the new API call keeps the two in step.

## Features with no backend today

- Faculty: Attendance Correction / Amendment Request. New backend: request doctype, approval workflow, APIs.

- Parent: Multi-Ward Switcher (if more than one child enrolled). Web shows one ward. Backend must list all wards for a guardian and scope every parent API by ward.

- Parent: Ward Daily & Weekly Timetable (Read-Only). Reuses calendar widget; backend must allow guardian access to ward calendar.

- Parent: Campus Gate Entry. Assumed: ward's gate entry/exit log from RFID data. Scope must be confirmed.

- Parent: Hostel Room & Warden Contact Details. Expose ward hostel data to guardian; tap-to-call warden.

- Parent: University Notices & Parent Circulars. Needs audience targeting for parents (new field or doctype).

# 4. Approach

## App structure

- One app for all three roles. The role (Student, Faculty, Guardian) is read from the logged-in user, and a user with more than one role can switch.

- Flutter with Riverpod or Bloc for state, GoRouter for navigation and Dio for HTTP calls to Frappe /api/method endpoints using token authentication.

- Shared widgets are built once and reused: the calendar (Student, Faculty and Parent timetables), attendance and results views (Student and Parent), venue booking (Student and Faculty) and Razorpay payments (Student and Parent).

- Firebase Cloud Messaging for push alerts such as low attendance, fee dues, results and announcements.

## Helpdesk

Today each portal loads /helpdesk/my-tickets in an iframe. In the app the same page opens in an authenticated WebView: the app passes the Frappe session to the WebView so the user is not asked to log in again, hides the helpdesk sidebar for small screens, and supports file attachments and links to a specific ticket. This is the fastest route and keeps one helpdesk to maintain. It is included in the estimate (shared shell in Common, about half a day to a day per portal).

A fully native helpdesk screen built on the Helpdesk app's APIs would give a smoother experience, but adds about 12 to 15 days. It can follow in a later release.

## How the estimate was built

Each feature is sized in person-days across three tracks: Flutter UI, backend/API work, and QA and integration. Complexity is S, M or L. Common work (setup, design, authentication, notifications, payments, file handling, release) is estimated once in the Common Foundation module instead of being repeated in each portal.

Feature days in the tables below are sized for an experienced developer, as is standard. The team figures then apply a 1.5x factor for junior developers, plus 10 days of learning per person, so the per-feature sizing stays comparable if the team changes.

# 5. Common Foundation

Work that every portal depends on. It is done first and is shared, so the portal estimates below assume it exists.

| # | Feature | API | Size | UI | Backend | QA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project setup, architecture, flavours (dev/UAT/prod), CI/CD | - | M | 4.0 | 0.0 | 1.0 | 5.0 |
| 2 | Mobile UI/UX design: design system, theme, dark mode, shared widgets | - | L | 8.0 | 0.0 | 1.0 | 9.0 |
| 3 | API client layer: Dio, Frappe auth headers, error handling, pagination, models | - | M | 4.0 | 0.0 | 1.0 | 5.0 |
| 4 | Authentication: login, forgot/reset password, token/session, role detection, biometric unlock | Partial | M | 4.0 | 2.0 | 1.5 | 7.5 |
| 5 | Role-based app shell and navigation (Student / Faculty / Parent in one app) | - | M | 2.0 | 0.0 | 1.0 | 3.0 |
| 6 | Push notifications (FCM) and in-app notification centre | Partial | M | 2.5 | 3.0 | 1.0 | 6.5 |
| 7 | File handling: camera/gallery/document upload, PDF download, view and share | Ready | M | 2.5 | 0.5 | 1.0 | 4.0 |
| 8 | Razorpay Flutter SDK integration (shared by Student and Parent payments) | Ready | M | 2.0 | 1.0 | 1.5 | 4.5 |
| 9 | Helpdesk WebView shell with single sign-on (replaces iframe) | Partial | M | 2.0 | 1.5 | 1.0 | 4.5 |
| 10 | Offline caching and connectivity handling | - | M | 3.0 | 0.0 | 1.0 | 4.0 |
| 11 | Security: secure storage, SSL pinning, session timeout, root/jailbreak checks | - | S | 1.5 | 0.0 | 0.5 | 2.0 |
| 12 | Crash reporting and analytics (Firebase Crashlytics/Analytics) | - | S | 1.0 | 0.0 | 0.5 | 1.5 |
| 13 | App Store and Play Store release: signing, listings, privacy forms, review cycles | - | M | 3.0 | 0.0 | 1.0 | 4.0 |
|  | Module total (base) |  |  | 39.5 | 8.0 | 13.0 | 60.5 |

Days above are for an experienced developer. With UAT, coordination and contingency: 81.7 days; for the junior team: 122.5 days, about 2.9 months with 2 developers. Notes for each feature are in the "Common Foundation" sheet of the workbook.

# 6. Student Portal

The largest module. Fee payments, venue booking and the dashboard carry the most effort. Most read screens need a JSON endpoint built from the existing get_context logic.

| # | Feature | API | Size | UI | Backend | QA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Home Dashboard: CGPA, Attendance, Fee Balance, Today's Schedule | Partial | M | 3.0 | 2.0 | 1.5 | 6.5 |
| 2 | My Courses & Enrolled Subjects | Partial | S | 2.0 | 1.0 | 1.0 | 4.0 |
| 3 | Daily & Weekly Timetable | Ready | M | 3.0 | 0.5 | 1.0 | 4.5 |
| 4 | Course-wise Attendance with Warning Alerts | Partial | M | 2.5 | 1.5 | 1.0 | 5.0 |
| 5 | Exam Eligibility Status per Course | Partial | S | 1.5 | 1.0 | 0.5 | 3.0 |
| 6 | Attendance Condonation / Excuse Application (with document upload) | Ready | M | 2.5 | 0.5 | 1.0 | 4.0 |
| 7 | General Academic Leave Application | Partial | S | 2.0 | 0.5 | 0.5 | 3.0 |
| 8 | Examination Schedule & Hall Ticket Download | Partial | M | 2.0 | 1.5 | 1.0 | 4.5 |
| 9 | Academic Results & Grade Cards | Partial | M | 2.5 | 1.5 | 1.0 | 5.0 |
| 10 | Grade Appeal / Re-evaluation Application | Partial | S | 2.0 | 0.5 | 1.0 | 3.5 |
| 11 | Re-Examination & Improvement Exam Registration + Fee Payment | Ready | M | 3.0 | 0.5 | 1.5 | 5.0 |
| 12 | Fee Demands, Scholarships & Online Payment (UPI, Card, Net Banking) | Partial | L | 5.0 | 1.5 | 2.5 | 9.0 |
| 13 | Payment Receipt Download | Ready | S | 1.0 | 0.3 | 0.5 | 1.8 |
| 14 | Hostel Room & Warden Details | Partial | S | 1.5 | 0.5 | 0.5 | 2.5 |
| 15 | Hostel Leave / Out-Pass Request | Partial | S | 2.0 | 0.5 | 0.5 | 3.0 |
| 16 | Hostel Maintenance Complaint (with photo upload) | Partial | S | 2.0 | 0.5 | 0.5 | 3.0 |
| 17 | Campus Venue Booking | Ready | L | 4.0 | 0.5 | 1.5 | 6.0 |
| 18 | Digital Student ID Card | Partial | M | 2.0 | 1.0 | 0.5 | 3.5 |
| 19 | Student Registration Slip Download | Ready | S | 1.0 | 0.3 | 0.5 | 1.8 |
| 20 | Bank Account Details Submission (for scholarships & refunds) | Ready | S | 1.5 | 0.3 | 0.5 | 2.3 |
| 21 | Helpdesk (WebView) | Partial | S | 1.0 | 0.3 | 0.5 | 1.8 |
| 22 | Notifications & Announcements | Partial | S | 1.5 | 0.5 | 0.5 | 2.5 |
| 23 | Profile view | Partial | S | 1.5 | 0.5 | 0.5 | 2.5 |
|  | Module total (base) |  |  | 50.0 | 17.5 | 20.0 | 87.5 |

Days above are for an experienced developer. With UAT, coordination and contingency: 118.1 days; for the junior team: 177.2 days, about 4.2 months with 2 developers. Notes for each feature are in the "Student Portal" sheet of the workbook.

# 7. Faculty Portal

Faculty APIs are the most complete, mainly because the dashboard drilldowns, attendance and marks entry are already API-driven. The effort is in usable mobile screens for bulk attendance and marks entry. Attendance correction is new.

| # | Feature | API | Size | UI | Backend | QA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Faculty Dashboard: Today's Classes, Pending Tasks, Announcements | Ready | M | 3.5 | 0.5 | 1.0 | 5.0 |
| 2 | My Assigned Courses & Student Roster | Partial | M | 2.5 | 1.0 | 1.0 | 4.5 |
| 3 | Class Attendance Recording (Present / Absent / On Duty) | Ready | L | 4.0 | 0.5 | 2.0 | 6.5 |
| 4 | Attendance Correction / Amendment Request | Missing | M | 2.0 | 3.0 | 1.0 | 6.0 |
| 5 | Marks & Assessment Entry | Ready | L | 5.0 | 0.5 | 2.0 | 7.5 |
| 6 | Student Leave & Condonation / Excuse Review & Recommendation | Partial | M | 2.5 | 1.0 | 1.0 | 4.5 |
| 7 | Weekly Timetable & Academic Calendar View | Ready | S | 1.5 | 0.3 | 0.5 | 2.3 |
| 8 | Campus Venue Booking | Ready | M | 2.0 | 0.5 | 1.0 | 3.5 |
| 9 | Course Announcements to Students | Partial | M | 2.0 | 1.0 | 0.5 | 3.5 |
| 10 | Helpdesk (WebView) | Partial | S | 0.5 | 0.3 | 0.5 | 1.3 |
| 11 | Profile, Settings & Change Password | Ready | S | 1.5 | 0.0 | 0.5 | 2.0 |
|  | Module total (base) |  |  | 27.0 | 8.5 | 11.0 | 46.5 |

Days above are for an experienced developer. With UAT, coordination and contingency: 62.8 days; for the junior team: 94.2 days, about 2.2 months with 2 developers. Notes for each feature are in the "Faculty Portal" sheet of the workbook.

# 8. Parent Portal

The parent web portal currently has four pages (dashboard, attendance, fees, results) for a single ward. Multi-ward support, timetable, gate entry, hostel details and notices need new backend work. Screens largely reuse Student widgets in read-only mode.

| # | Feature | API | Size | UI | Backend | QA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Multi-Ward Switcher (if more than one child enrolled) | Missing | M | 2.0 | 2.0 | 1.0 | 5.0 |
| 2 | Ward Academic Overview: Programme, Batch, CGPA | Partial | S | 2.0 | 1.0 | 0.5 | 3.5 |
| 3 | Course-wise Attendance Monitoring with Low-Attendance Alerts | Partial | M | 1.5 | 1.5 | 0.5 | 3.5 |
| 4 | Ward Daily & Weekly Timetable (Read-Only) | Missing | S | 1.0 | 1.0 | 0.5 | 2.5 |
| 5 | Campus Gate Entry | Missing | M | 2.0 | 3.0 | 1.0 | 6.0 |
| 6 | Fee Statement & Outstanding Dues | Partial | M | 2.5 | 0.5 | 1.0 | 4.0 |
| 7 | Online Fee Payment (UPI, Card, Net Banking) | Ready | M | 2.0 | 0.5 | 1.5 | 4.0 |
| 8 | Payment Receipt Download | Ready | S | 0.5 | 0.0 | 0.5 | 1.0 |
| 9 | Ward Academic Results & Grade History | Partial | S | 2.0 | 1.0 | 0.5 | 3.5 |
| 10 | Hostel Room & Warden Contact Details | Missing | S | 1.0 | 1.0 | 0.5 | 2.5 |
| 11 | University Notices & Parent Circulars | Missing | M | 1.5 | 1.5 | 0.5 | 3.5 |
| 12 | Helpdesk (WebView) | Partial | S | 0.5 | 0.5 | 0.5 | 1.5 |
|  | Module total (base) |  |  | 18.5 | 13.5 | 8.5 | 40.5 |

Days above are for an experienced developer. With UAT, coordination and contingency: 54.7 days; for the junior team: 82.0 days, about 2.0 months with 2 developers. Notes for each feature are in the "Parent Portal" sheet of the workbook.

# 9. Team and timeline

The team is 2 junior developers. There is no separate designer, backend developer or QA engineer, so both developers share all the work: Flutter screens, the new backend APIs, testing and store release. A sensible split is for one developer to lead the Flutter app and the other to build the backend APIs first and then join the Flutter work.

## Phased delivery

Because the same 2 people do everything, the phases run one after another. Each portal is released when its phase ends, so users get value before the whole app is finished.

| Phase | Effort (days) | Months | Months from start | Outcome |
| --- | --- | --- | --- | --- |
| Phase 0: Ramp-up and Common Foundation | 142.5 | 3.4 | 0.0 to 3.4 | Learning, app setup, login, design, payments, notifications, helpdesk WebView. |
| Phase 1: Student Portal | 177.2 | 4.2 | 3.4 to 7.6 | Student app goes live (first release). |
| Phase 2: Faculty Portal | 94.2 | 2.2 | 7.6 to 9.9 | Faculty features released. |
| Phase 3: Parent Portal | 82.0 | 2.0 | 9.9 to 11.8 | Full app with all three portals. |

Total: 495.9 person-days, about 12 months with 2 developers. The Student app can go live after about 8 months.

## Ways to shorten or de-risk the timeline

- Senior reviewer, part-time: A senior Flutter/Frappe developer for about 1 day a week to set the architecture, review code and guide the payment and security work. This is the single most effective way to protect quality and keep the junior factor close to 1.5x instead of 2x.

- Add a third developer: Each additional junior developer cuts the duration roughly in proportion; with 3 developers it is about 8 months.

- Reduce the first release: Launch the Student app first and start Faculty and Parent only after feedback. Parent features with no backend today (gate entry, notices, multi-ward) can move to a later release.

- Keep the WebView helpdesk: Keep the helpdesk as a WebView (included) instead of native screens.

# 10. Assumptions, exclusions and risks

## Assumptions

- One Flutter app for all three roles; the role is decided at login. Android and iOS from the same codebase.

- The Frappe backend stays the system of record. The mobile app calls whitelisted /api/method endpoints with token authentication.

- Helpdesk is delivered as an authenticated WebView of the existing /helpdesk portal (same approach as today's iframe). A fully native helpdesk would add about 12 to 15 days.

- Payments use the Razorpay Flutter SDK with the existing order/confirm endpoints and webhook.

- Feature estimates are sized for an experienced developer, then multiplied by the junior productivity factor (1.5x) for this team of 2 junior developers.

- The 2 developers do all work: Flutter screens, backend APIs, testing and store release. There is no separate QA, designer or backend developer.

- Each developer gets 10 days of ramp-up to learn Flutter, the Frappe APIs, the Razorpay SDK and store release.

- Mobile screens follow the existing web portal design, so no separate UI/UX designer is needed.

## Exclusions

- Placement, Transcript Request, Fee Certificate, Enrollment and Documents pages that exist in the web portal but are not in the requested scope.

- Admin/staff features, tablet-specific layouts, multiple languages, Apple/Google developer account fees.

## Risks

- Many read screens rely on get_context. Each needs a new JSON endpoint; logic must be shared with the web page to avoid two versions drifting apart.

- Campus Gate Entry scope is undefined (view logs, QR pass, or live alerts). Estimated as a read-only log from RFID data.

- Parent portal currently supports a single ward. Multi-ward needs changes to every parent endpoint's permission checks.

- Helpdesk WebView depends on cookie sharing and the helpdesk UI fitting small screens; iOS WebView cookie handling needs early testing.

- App Store review for apps with payments and login can take several rounds.

- Junior team without senior review: architecture, security (token storage, payments) and code quality issues may surface late. A senior developer reviewing for about 1 day a week is strongly recommended.

- With only 2 people, leave, illness or attrition directly delays delivery; there is no backup.

- Developers testing their own work miss more defects. Plan UAT with real students, faculty and parents before each release.

# 11. Decisions needed before kick-off

- Campus Gate Entry scope: what parents should see: an entry/exit log, live alerts, or a QR pass. The estimate assumes a read-only log from RFID data.

- Helpdesk approach: WebView (included) or native screens (12 to 15 extra days).

- Hostel out-pass: whether a QR out-pass scanned at the gate is needed (about 2 extra days).

- Release order: whether parent features go live with the first release or in a second release after Student and Faculty.

- Store accounts: Apple and Google developer accounts in the university's name, and the app name and branding.

- Senior support: whether a senior developer can review the juniors' work part-time.