## Summary
SLCM Mobile App (Flutter): Effort Estimation Summary
Team: 2 junior developers covering Flutter, backend and testing. Effort is in person-days: one person working one day. Prepared 15 Oct 2026.
Assumptions (edit the yellow cells)
UAT support & bug-fix allowance | 10% | Share of base effort for UAT rounds and fixes.
Project coordination & meetings | 10% | Share of base effort for stand-ups, reviews, coordination.
Contingency | 15% | Buffer for unknowns: unclear scope (e.g. Gate Entry), store review delays.
Team size (developers) | 2 | Both developers share Flutter, backend and testing work.
Junior productivity factor | 1.5 | Base estimates assume an experienced developer. Juniors typically take 1.5x to 2x as long.
Ramp-up / learning days per person | 10 | Learning Flutter, Frappe APIs, Razorpay SDK and store release before productive work.
Working days per month | 21
Effort by module (person-days)
Module | Features | Flutter UI | Backend / API | QA & Integration | Base effort | UAT & bug-fix | Coordination | Contingency | Total (experienced developer) | Total for junior team | Calendar months (team of 2)
Common Foundation | 13
Student Portal | 23
Faculty Portal | 11
Parent Portal | 12
Ramp-up & learning (both developers)
Grand total
Total for junior team = experienced-developer total x junior factor. Calendar months = junior-team days / (team size x working days per month).
Headline
Total effort for the junior team (person-days)
Calendar duration with 2 developers (months)
Calendar duration with 2 developers (weeks)
Phased plan (both developers work through the phases in order)
Phase | Effort for junior team (days) | Calendar months | Cumulative months | Outcome
Phase 0: Ramp-up + Common Foundation |  |  |  | Login, app shell, design, payments, notifications, helpdesk WebView ready.
Phase 1: Student Portal |  |  |  | Student app can go live (first release).
Phase 2: Faculty Portal |  |  |  | Faculty features released.
Phase 3: Parent Portal |  |  |  | Full app with all three portals.
API readiness by module (feature count)
Module | Ready | Partial | Missing
Student Portal
Faculty Portal
Parent Portal
Ready = JSON API exists. Partial = action API exists but list/read data is only in server-rendered get_context. Missing = no backend in the web portal today.

## Common Foundation
Common Foundation: Flutter Mobile App Effort Estimate
Effort in person-days. Yellow cells are estimates you can change; totals recalculate.
# | Feature | Web source | Existing API(s) | API readiness | Complexity | Flutter UI (days) | Backend / API (days) | QA & Integration (days) | Total (days) | Notes
1 | Project setup, architecture, flavours (dev/UAT/prod), CI/CD | - | - | - | M | 4 | 0 | 1 |  | Flutter 3.x, Riverpod/Bloc, GoRouter, Codemagic or GitHub Actions builds for Android and iOS.
2 | Mobile UI/UX design: design system, theme, dark mode, shared widgets | Existing web portal styling | - | - | L | 8 | 0 | 1 |  | Includes Figma screens for ~45 screens and reusable cards, tables, calendar and form widgets.
3 | API client layer: Dio, Frappe auth headers, error handling, pagination, models | - | - | - | M | 4 | 0 | 1 |  | Typed models for every endpoint; central handling of Frappe exceptions and session expiry.
4 | Authentication: login, forgot/reset password, token/session, role detection, biometric unlock | Frappe login | user.py (login/reset) | Partial | M | 4 | 2 | 1.5 |  | Backend: issue API key/secret or OAuth token for mobile; endpoint returning role(s) and linked Student/Instructor/Guardian.
5 | Role-based app shell and navigation (Student / Faculty / Parent in one app) | _base.html per portal | - | - | M | 2 | 0 | 1 |  | One app, role chosen at login. Users with more than one role get a role switcher.
6 | Push notifications (FCM) and in-app notification centre | notifications.html | get_portal_notifications, get_faculty_notifications | Partial | M | 2.5 | 3 | 1 |  | Backend: device token doctype, FCM sender hooked into Notification Log / alerts (attendance, fees, results).
7 | File handling: camera/gallery/document upload, PDF download, view and share | Multiple pages | upload_file, download_* endpoints | Ready | M | 2.5 | 0.5 | 1 |  | Shared by condonation, complaints, bank passbook, receipts, hall ticket and grade cards.
8 | Razorpay Flutter SDK integration (shared by Student and Parent payments) | fees.html (Razorpay checkout.js) | create_*_order / confirm_* / sync_payment_status | Ready | M | 2 | 1 | 1.5 |  | Native SDK replaces checkout.js. Backend: verify signatures for mobile flow; webhook already exists.
9 | Helpdesk WebView shell with single sign-on (replaces iframe) | support.html (iframe to /helpdesk/my-tickets) | Helpdesk app (Frappe) | Partial | M | 2 | 1.5 | 1 |  | Inject Frappe session cookie into WebView, hide helpdesk sidebar via CSS, handle deep links to tickets and file attachments.
10 | Offline caching and connectivity handling | - | - | - | M | 3 | 0 | 1 |  | Cache timetable, ID card, results and attendance for offline view.
11 | Security: secure storage, SSL pinning, session timeout, root/jailbreak checks | - | - | - | S | 1.5 | 0 | 0.5
12 | Crash reporting and analytics (Firebase Crashlytics/Analytics) | - | - | - | S | 1 | 0 | 0.5
13 | App Store and Play Store release: signing, listings, privacy forms, review cycles | - | - | - | M | 3 | 0 | 1 |  | Apple review can take several rounds; plan buffer.
Module total

## Student Portal
Student Portal: Flutter Mobile App Effort Estimate
Effort in person-days. Yellow cells are estimates you can change; totals recalculate.
# | Feature | Web source | Existing API(s) | API readiness | Complexity | Flutter UI (days) | Backend / API (days) | QA & Integration (days) | Total (days) | Notes
1 | Home Dashboard: CGPA, Attendance, Fee Balance, Today's Schedule | student-portal/index.py | None (get_context only) | Partial | M | 3 | 2 | 1.5 |  | Needs one aggregated dashboard JSON endpoint built from index.py logic.
2 | My Courses & Enrolled Subjects | student-portal/courses.py | None (get_context only) | Partial | S | 2 | 1 | 1 |  | Expose course list and enrolment from courses.py.
3 | Daily & Weekly Timetable | student-portal/timetable.py | get_student_calendar | Ready | M | 3 | 0.5 | 1 |  | Day/week calendar widget, reused by Faculty and Parent.
4 | Course-wise Attendance with Warning Alerts | student-portal/attendance.py | None (get_context only) | Partial | M | 2.5 | 1.5 | 1 |  | Expose attendance summary; push alert when below threshold.
5 | Exam Eligibility Status per Course | attendance.py / exam_schedule.py | None (get_context only) | Partial | S | 1.5 | 1 | 0.5 |  | Expose eligibility flags already computed for the web.
6 | Attendance Condonation / Excuse Application (with document upload) | attendance.html | get_condonation_reasons, submit_condonation_application, submit_fa_mfa_application | Ready | M | 2.5 | 0.5 | 1 |  | Form with camera/document picker and application status list.
7 | General Academic Leave Application | student-portal/leave_request.py | submit_leave_request (www) | Partial | S | 2 | 0.5 | 0.5 |  | Submit API exists; add a list/status endpoint.
8 | Examination Schedule & Hall Ticket Download | student-portal/exam_schedule.py | None (get_context only) | Partial | M | 2 | 1.5 | 1 |  | Expose schedule and hall ticket PDF endpoint.
9 | Academic Results & Grade Cards | student-portal/results.py | None (get_context only) | Partial | M | 2.5 | 1.5 | 1 |  | Semester-wise results, SGPA/CGPA, grade card PDF.
10 | Grade Appeal / Re-evaluation Application | student-portal/grade_appeal.py | submit_appeal (www) | Partial | S | 2 | 0.5 | 1 |  | Submit exists; add appeal list/status endpoint.
11 | Re-Examination & Improvement Exam Registration + Fee Payment | student-portal/re_exam.py | initiate_re_exam_registration, initiate_improvement_exam_registration, *_payment_order | Ready | M | 3 | 0.5 | 1.5 |  | Uses shared Razorpay module; payment test cases.
12 | Fee Demands, Scholarships & Online Payment (UPI, Card, Net Banking) | student-portal/fees.py (1,117 lines) | student_payment.py (32 endpoints), get_invoice_summary | Partial | L | 5 | 1.5 | 2.5 |  | Payment APIs ready; fee list and scholarship view need a JSON endpoint. Single, bulk and demand payments.
13 | Payment Receipt Download | fees.html | download_fee_receipt, download_re_exam_receipt, download_improvement_exam_receipt | Ready | S | 1 | 0.25 | 0.5
14 | Hostel Room & Warden Details | student-portal/hostel.py | None (get_context only) | Partial | S | 1.5 | 0.5 | 0.5
15 | Hostel Leave / Out-Pass Request | student-portal/hostel.py | submit_leave_request (hostel) | Partial | S | 2 | 0.5 | 0.5 |  | Add list/status endpoint. A QR out-pass for gate scanning would add ~2 days.
16 | Hostel Maintenance Complaint (with photo upload) | student-portal/hostel.py | submit_complaint | Partial | S | 2 | 0.5 | 0.5 |  | Add complaint list/status endpoint.
17 | Campus Venue Booking | student-portal/venue_booking.py | check_room_availability, get_rooms_for_type, submit_venue_booking, cancel_venue_booking, request_venue_swap | Ready | L | 4 | 0.5 | 1.5 |  | Availability search, booking, swap and cancel. Widgets reused by Faculty.
18 | Digital Student ID Card | documents.py / profile.py | None (get_context only) | Partial | M | 2 | 1 | 0.5 |  | Card with photo and QR, available offline.
19 | Student Registration Slip Download | student-portal/documents.html | download_student_document | Ready | S | 1 | 0.25 | 0.5
20 | Bank Account Details Submission (for scholarships & refunds) | student-portal/profile.html | submit_bank_details, upload_bank_passbook | Ready | S | 1.5 | 0.25 | 0.5
21 | Helpdesk (WebView) | student-portal/support.html (iframe) | Helpdesk app | Partial | S | 1 | 0.25 | 0.5 |  | Uses the shared WebView shell from the Common module.
22 | Notifications & Announcements | notifications.html / announcements.py | get_portal_notifications | Partial | S | 1.5 | 0.5 | 0.5 |  | Announcement list needs a JSON endpoint.
23 | Profile view | student-portal/profile.py | add_guardian | Partial | S | 1.5 | 0.5 | 0.5 |  | Not in the requested list, but needed in any mobile app.
Module total

## Faculty Portal
Faculty Portal: Flutter Mobile App Effort Estimate
Effort in person-days. Yellow cells are estimates you can change; totals recalculate.
# | Feature | Web source | Existing API(s) | API readiness | Complexity | Flutter UI (days) | Backend / API (days) | QA & Integration (days) | Total (days) | Notes
1 | Faculty Dashboard: Today's Classes, Pending Tasks, Announcements | faculty-portal/index.py | get_dashboard_stats, drilldown_todays_classes, drilldown_pending_attendance | Ready | M | 3.5 | 0.5 | 1
2 | My Assigned Courses & Student Roster | faculty-portal/course-offerings.py | drilldown_subjects, drilldown_students, drilldown_student_groups | Partial | M | 2.5 | 1 | 1
3 | Class Attendance Recording (Present / Absent / On Duty) | faculty-portal/attendance.py | get_session_students, save_attendance, bulk_attendance.* | Ready | L | 4 | 0.5 | 2 |  | Fast bulk marking UX, mark-all, offline queue with sync.
4 | Attendance Correction / Amendment Request | Not in web portal | None | Missing | M | 2 | 3 | 1 |  | New backend: request doctype, approval workflow, APIs.
5 | Marks & Assessment Entry | faculty-portal/marks.py | faculty_assessment_marks.* (5), faculty_grades.* (11), save_student_marks | Ready | L | 5 | 0.5 | 2 |  | Grid entry on small screens is the hardest UX in the app; validation and draft save.
6 | Student Leave & Condonation / Excuse Review & Recommendation | faculty-portal/index.py (drilldowns) | drilldown_condonation, save_condonation_recommendation | Partial | M | 2.5 | 1 | 1 |  | Leave review list needs an endpoint; attachment preview.
7 | Weekly Timetable & Academic Calendar View | faculty-portal/my_classes.py | get_faculty_calendar | Ready | S | 1.5 | 0.25 | 0.5 |  | Reuses the Student calendar widget.
8 | Campus Venue Booking | faculty-portal/venue_booking.py | create_venue_booking, check_room_availability | Ready | M | 2 | 0.5 | 1 |  | Reuses Student venue booking widgets.
9 | Course Announcements to Students | faculty-portal/communication.py | None (get_context only) | Partial | M | 2 | 1 | 0.5 |  | Compose/list endpoint; triggers student push notification.
10 | Helpdesk (WebView) | faculty-portal/support.html (iframe) | Helpdesk app | Partial | S | 0.5 | 0.25 | 0.5
11 | Profile, Settings & Change Password | faculty-portal/profile.py, settings.py | update_profile, change_password, save_preferences | Ready | S | 1.5 | 0 | 0.5 |  | Not in the requested list, but needed in any mobile app.
Module total

## Parent Portal
Parent Portal: Flutter Mobile App Effort Estimate
Effort in person-days. Yellow cells are estimates you can change; totals recalculate.
# | Feature | Web source | Existing API(s) | API readiness | Complexity | Flutter UI (days) | Backend / API (days) | QA & Integration (days) | Total (days) | Notes
1 | Multi-Ward Switcher (if more than one child enrolled) | parent-portal (single ward only) | None | Missing | M | 2 | 2 | 1 |  | Web shows one ward. Backend must list all wards for a guardian and scope every parent API by ward.
2 | Ward Academic Overview: Programme, Batch, CGPA | parent-portal/index.py | None (get_context only) | Partial | S | 2 | 1 | 0.5
3 | Course-wise Attendance Monitoring with Low-Attendance Alerts | parent-portal/attendance.py | None (get_context only) | Partial | M | 1.5 | 1.5 | 0.5 |  | Reuses Student attendance widgets; push alert to parent.
4 | Ward Daily & Weekly Timetable (Read-Only) | Not in parent web portal | get_student_calendar (student-scoped) | Missing | S | 1 | 1 | 0.5 |  | Reuses calendar widget; backend must allow guardian access to ward calendar.
5 | Campus Gate Entry | Not in web portal | None | Missing | M | 2 | 3 | 1 |  | Assumed: ward's gate entry/exit log from RFID data. Scope must be confirmed.
6 | Fee Statement & Outstanding Dues | parent-portal/fees.py | parent_get_invoice_summary | Partial | M | 2.5 | 0.5 | 1
7 | Online Fee Payment (UPI, Card, Net Banking) | parent-portal/fees.html | parent_create_payment_order, parent_confirm_fee_payment, parent_*_demand_payment | Ready | M | 2 | 0.5 | 1.5 |  | Uses shared Razorpay module.
8 | Payment Receipt Download | parent-portal/fees.html | parent_download_fee_receipt, parent_download_fee_invoice | Ready | S | 0.5 | 0 | 0.5
9 | Ward Academic Results & Grade History | parent-portal/results.py | None (get_context only) | Partial | S | 2 | 1 | 0.5 |  | Reuses Student results widgets.
10 | Hostel Room & Warden Contact Details | Not in parent web portal | None | Missing | S | 1 | 1 | 0.5 |  | Expose ward hostel data to guardian; tap-to-call warden.
11 | University Notices & Parent Circulars | Not in parent web portal | None | Missing | M | 1.5 | 1.5 | 0.5 |  | Needs audience targeting for parents (new field or doctype).
12 | Helpdesk (WebView) | No parent support page found | Helpdesk app | Partial | S | 0.5 | 0.5 | 0.5 |  | Guardian users need helpdesk access configured.
Module total

## Assumptions & Risks
Assumptions, Exclusions & Risks
# | Type | Detail
1 | Assumption | One Flutter app for all three roles; the role is decided at login. Android and iOS from the same codebase.
2 | Assumption | The Frappe backend stays the system of record. The mobile app calls whitelisted /api/method endpoints with token authentication.
3 | Assumption | Helpdesk is delivered as an authenticated WebView of the existing /helpdesk portal (same approach as today's iframe). A fully native helpdesk would add about 12 to 15 days.
4 | Assumption | Payments use the Razorpay Flutter SDK with the existing order/confirm endpoints and webhook.
5 | Assumption | Feature estimates are sized for an experienced developer, then multiplied by the junior productivity factor (1.5x) for this team of 2 junior developers.
6 | Assumption | The 2 developers do all work: Flutter screens, backend APIs, testing and store release. There is no separate QA, designer or backend developer.
7 | Assumption | Each developer gets 10 days of ramp-up to learn Flutter, the Frappe APIs, the Razorpay SDK and store release.
8 | Assumption | Mobile screens follow the existing web portal design, so no separate UI/UX designer is needed.
9 | Exclusion | Placement, Transcript Request, Fee Certificate, Enrollment and Documents pages that exist in the web portal but are not in the requested scope.
10 | Exclusion | Admin/staff features, tablet-specific layouts, multiple languages, Apple/Google developer account fees.
11 | Risk | Many read screens rely on get_context. Each needs a new JSON endpoint; logic must be shared with the web page to avoid two versions drifting apart.
12 | Risk | Campus Gate Entry scope is undefined (view logs, QR pass, or live alerts). Estimated as a read-only log from RFID data.
13 | Risk | Parent portal currently supports a single ward. Multi-ward needs changes to every parent endpoint's permission checks.
14 | Risk | Helpdesk WebView depends on cookie sharing and the helpdesk UI fitting small screens; iOS WebView cookie handling needs early testing.
15 | Risk | App Store review for apps with payments and login can take several rounds.
16 | Risk | Junior team without senior review: architecture, security (token storage, payments) and code quality issues may surface late. A senior developer reviewing for about 1 day a week is strongly recommended.
17 | Risk | With only 2 people, leave, illness or attrition directly delays delivery; there is no backup.
18 | Risk | Developers testing their own work miss more defects. Plan UAT with real students, faculty and parents before each release.